## Role of Member
Assigned Task
Member | Role
Trung (trungnd69) | Provisioned
Bac (bacnm) | Switch, CTL light and OTA secure
Duc (ducnv74) | Light, CTL light and OTA secure
Hieu (hieuhv18) | motion sensor,EM2, gateway,moblieapp

## Weekly Schedule
Sprint | Date | Task | Duty people | Output this week | Result last week
(Công việc phải hoàn thành)
Week 1 | 26/6 - 30/6 | _ Mượn mạch (5 mạch + 2 sensor motion) _ tổng hợp tài liệu _ bluetooth technology
Week 2 | 3/7-7/7 | _ Write BLE MESH theory (in notebook on onedrive) _ Ass1: Demo example SoC Light _ Ass2: Demo example Switch _ Ass3: Demo example Sensor Server and Sensor Client (Operation in mode EM2 theory) _ Ass4: Provisioner for devices join network by button | _ Trung: Ass4 _ Bắc: Ass 2 _ Đức: Ass 1 _ Hiếu: Ass 3 | _ Understand and reimplement from example bluetooth mesh _ Combine 4 project to a network mesh | None
Week 3 | 10/7-14/7 | _ Ass 1: Provisioner for devices join network by button _ Ass 2: Gateway communicate with UART to control light and notify when motion sensor have signal _ Ass 3: Write flow provisioned, flow light, switch and motion sensor _ Ass 4: Light using PWM to subtitute CTL light _ Ass 5: Light send message Heartbeat _ Ass 6: Run Motion Sensor and Switch with mode EM2 | _ Đức and Bắc: + Monday and Tuesday: understand guiline demo. Sychronization between device and app to turn on, turn off led. Reference by demo example switch and light combine with write word flow of program to presentation (do Ass 3) _ Đức: Ass 4 _ Bắc: Ass5 _ Trung: Ass 1 _ Hiếu: Ass 6 and Ass 3 | _ Create network with 2 group and finish operation node in networks: Light, Switch, Motion Sensor and GateWay _ Can provisioner for device join network by button | _ Đức, Bắc: need time to finish assignment _ Trung: Start implement example provisioner _ Hiếu: Done demo sensor motion by turn on off led
Week 4 | 17/7-21/7 | _ Ass 1: Provisioner for 2 devices join network by 2 button _ Ass 2: After provisioner, config node by provisioner _ Ass 3: Create gate way _ Ass 4: Mobile app communicate with metheo PB-GATT _ Ass 5: update OTA nonsecure | _ Đức and Bắc: learn about update OTA non-secure _ Trung: Ass 1 and Ass 2 _ Hiếu: try finish run mode EM2; do Ass3 and Ass 4 | _Create a network with 2 groups and finish operation node in networks: Light, Switch, Motion Sensor, and GateWay _ Update OTA non-secure | _ Đức, Bắc: finish demo light and switch _ Trung: provisioner success for devices joining the network but still not unstable _ Hiếu: Trouble when running node in mode EM2
Week 5 | 24/7-28/7 | _ Ass 1: Finish Provisioner for all devices join networks by button. Distinguish when the device is in group 1 group 2 or the gateway _ Ass 2: Finish update OTA secure _ Ass 3: Finish gateway to find all lights in the network _Ass4: Mobile app communicates with the PB-GATT | _ Đức and Bắc: learn about update OTA secure _ Trung: Ass 1 _ Hiếu: do Ass3 and Ass 4 | _ Success provides all devices join the mesh network to test the project operation and function of each node _ Update secure | _ Đức, Bắc: finish demo update OTA non-secure _ Trung: provisioner success for devices join to network and stable _ Hiếu: Trouble when running node in mode EM2
Week 6 | 31/7-4/8 | _ System Test each role of a node _ Write Document _ Write Slide and Architecture System